## Sprint 1
Sprint | General Task | Detailed Task | Story Points | Effort | Status | Total SP (GT)
Sprint 1 | GT-1.0: Platform First-Run Setup | 1.0.1: system_config table | 2 | ~1h | ✅ | 25
|  | 1.0.2: SuperAdmin UserRole enum | 1 | ~1h | ✅
|  | 1.0.3: Setup API endpoints | 5 | ~3h | ✅
|  | 1.0.4: Bootstrap detection middleware | 3 | ~2h | ✅
|  | 1.0.5: Next.js middleware setup state | 2 | ~1h | ✅
|  | 1.0.6: Setup wizard UI | 8 | ~4h | ✅
|  | 1.0.7: Super Admin login page | 2 | ~1h | ✅
|  | 1.0.8: RabbitMQ platform.setup.completed event | 1 | ~1h | ✅
|  | 1.0.9: SETUP_SECRET_KEY env variable | 1 | ~0.5h | ✅
Sprint 1 | GT-1.1: Project Infrastructure Setup | 1.1.1: Initialize monorepo structure | 3 | ~2h | ✅ | 15
|  | 1.1.2: Shared Python packages | 5 | ~3h | ✅
|  | 1.1.3: PostgreSQL + pg0 setup | 3 | ~2h | ✅
|  | 1.1.4: MinIO object storage setup | 2 | ~1h | ✅
|  | 1.1.5: RabbitMQ setup | 2 | ~1h | ✅
Sprint 1 | GT-1.2: RabbitMQ Message Broker Configuration | 1.2.1: RabbitMQ exchanges and queues | 3 | ~2h | ✅ | 6
|  | 1.2.2: Message publisher/subscriber utilities | 3 | ~2h | ✅
Sprint 1 | GT-1.3: API Gateway (Traefik v3) | 1.3.1: Traefik v3 gateway | 3 | ~2h | ✅ | 3
Sprint 1 | GT-1.4: MS1 Identity & Access Service | 1.4.1: Initialize FastAPI service | 3 | ~2h | ✅ | 47
|  | 1.4.2: Azure Entra ID integration | 5 | ~3h | ✅
|  | 1.4.3: Local admin authentication | 3 | ~2h | ✅
|  | 1.4.4: JWT token management | 3 | ~2h | ✅
|  | 1.4.5: RBAC middleware | 3 | ~2h | ✅
|  | 1.4.6: User management endpoints | 5 | ~3h | ✅
|  | 1.4.7: Admin user invite endpoint | 3 | ~2h | ✅
|  | 1.4.8: Admin user management UI | 8 | ~5h | ✅
|  | 1.4.9: Admin user action backend endpoints (Post-Sprint enhancement) | 3 | ~2h | ✅
|  | 1.4.10: Bulk user import via CSV | 3 | ~2h | ✅
|  | 1.4.11: Export user list | 3 | ~2h | ✅
|  | 1.4.12: Onboarding flow backend | 5 | ~3h | ✅
Sprint 1 | GT-1.13: Multi-Tenancy Infrastructure | 1.13.1: Tenant entity and database schema | 3 | ~2h | ✅ | 31
|  | 1.13.2: Tenant CRUD API (Super Admin) | 5 | ~3h | ✅
|  | 1.13.3: JWT with tenantId + Traefik tenant middleware | 3 | ~2h | ✅
|  | 1.13.4: PostgreSQL RLS policies | 3 | ~2h | ✅
|  | 1.13.5: Tenant resolution on login flow | 3 | ~2h | ✅
|  | 1.13.6: Super Admin UI pages | 8 | ~5h | ✅
|  | 1.13.7: Tenant context indicator in Sidebar | 3 | ~2h | ✅
|  | 1.13.8: Tenant resolution on login page | 3 | ~2h | ✅
Sprint 1 | GT-1.14: Tenant-Scoped Identity Endpoints (Tenant Admin Access) | 1.14.1: Pending users endpoint | 3 | ~2h | ✅ | 24
|  | 1.14.2: User role override endpoint | 2 | ~1h | ✅
|  | 1.14.3: User status change endpoint | 2 | ~1h | ✅
|  | 1.14.4: User revocation endpoint | 2 | ~1h | ✅
|  | 1.14.5: Role mapping rules CRUD endpoints | 5 | ~3h | ✅
|  | 1.14.6: Role mapping simulation endpoint | 2 | ~1h | ✅
|  | 1.14.7: Identity audit log endpoint | 3 | ~2h | ✅
|  | 1.14.8: Email mismatches endpoint (NEW) | 2 | ~1h | ✅
|  | 1.14.9: Confirm email update endpoint (NEW) | 2 | ~1h | ✅
|  | 1.14.10: Keep email endpoint (NEW) | 1 | ~1h | ✅
Sprint 1 | GT-1.15: Super Admin Identity Management (Tenant Admin Accounts Only) | 1.15.1: Super Admin tenant admin list endpoint | 3 | ~2h | ✅ | 20
|  | 1.15.2: Assign tenant admin endpoint | 3 | ~2h | ✅
|  | 1.15.3: Unassign/revoke admin endpoint | 2 | ~1h | ✅
|  | 1.15.4: Suspend/reactivate admin endpoint | 2 | ~1h | ✅
|  | 1.15.5: Reset admin password endpoint | 2 | ~1h | ✅
|  | 1.15.6: Admin role mapping rules (platform-level) | 5 | ~3h | ✅
|  | 1.15.7: Admin audit log endpoint | 3 | ~2h | ✅
Sprint 1 | GT-1.16: Entra ID Field Mapping Database Migrations | 1.16.1: Add User fields for Entra ID sync | 0 |  | ✅ | 5
|  | 1.16.2: Add partial index for email mismatch queries | 1 | ~0.5h | ✅
|  | 1.16.3: Update User model and schemas | 3 | ~2h | ✅
|  | 1.16.4: Add timezone field to users table | 1 | ~0.5h | ✅
Sprint 1 | GT-1.17: Complete UserSyncService Implementation | 1.17.1: Implement 9-step UserSyncService | 0 |  | ✅ | 4
|  | 1.17.2: Add sync job scheduler | 2 | ~2h | ✅
|  | 1.17.3: Sync status dashboard | 2 | ~2h | ✅
Sprint 1 | GT-1.5: CI/CD Pipeline | 1.5.1: GitHub Actions workflow | 2 | ~1h | ✅ | 2
Sprint 1 | GT-1.6: Frontend UI — Project Scaffold & Auth | 1.6.1: Next.js project scaffold | 3 | ~2h | ✅ | 16
|  | 1.6.2: Login page with dual auth UI | 5 | ~3h | ✅
|  | 1.6.3: Sidebar and app shell layout | 5 | ~3h | ✅
|  | 1.6.4: Auth context and API client setup | 3 | ~2h | ✅
Sprint 1 | GT-1.7: Testing — Identity & Access (PENDING RENUMBER) | 1.7.1: Auth service unit tests | 5 | ~3h | ✅ | 8
|  | 1.7.2: API Gateway → Identity integration test | 3 | ~2h | ✅
Sprint 1 | GT-1.8: UI Design System Document | 1.8.1: UI design system documentation | 5 | ~3h | ✅ | 5
Sprint 1 | GT-1.9: Profile Page & Gamification Components | 1.9.1: Profile page with gamification widgets | 8 | ~4h | ✅ | 16
|  | 1.9.2: LevelBadge component | 2 | ~1h | ✅
|  | 1.9.3: XPProgressBar component | 2 | ~1h | ✅
|  | 1.9.4: AchievementBadge component | 2 | ~1h | ✅
|  | 1.9.5: ActivityHeatmap component | 1 | ~1h | ✅
|  | 1.9.6: RoleSwitcher component | 1 | ~0.5h | ✅
Sprint 1 | GT-1.10: Settings Page | 1.10.1: Settings page with tabs and Platform Admin sections | 8 | ~5h | ✅ | 13
|  | 1.10.2: Settings UI components (Badge, Switch, Tabs, Textarea, Select) | 5 | ~2h | ✅
Sprint 1 | GT-1.11: Admin Seed Script | 1.11.1: Admin user database seed script | 1 | ~0.5h | ✅ | 1
Sprint 1 | GT-1.12: Learning Service Backend (Sprint 2 Pre-Done) | 1.12.1: Course CRUD API | 5 | ~3h | ✅ | 19
|  | 1.12.2: Module & Lesson CRUD API | 5 | ~3h | ✅
|  | 1.12.3: Enrollment API with RabbitMQ events | 3 | ~2h | ✅
|  | 1.12.4: Progress tracking API with RabbitMQ events | 3 | ~2h | ✅
|  | 1.12.5: Learning service Pydantic schemas | 2 | ~1.5h | ✅
|  | 1.12.6: Learning service FastAPI app initialization | 1 | ~0.5h | ✅
Sprint 1 | GT-1.18: Super Admin First-Login Getting Started Checklist | 1.18.1: system_config superadmin fields | 2 | ~1h | ✅ | 10
|  | 1.18.2: Super Admin checklist API endpoints | 3 | ~2h | ✅
|  | 1.18.3: Getting Started checklist UI component | 3 | ~2h | ✅
|  | 1.18.4: Super Admin first-login detection middleware | 2 | ~1h | ✅
Sprint 1 | GT-1.19: Super Admin Dashboard Full Widget Layout | 1.19.1: Stats cards row (4 cards) | 3 | ~2h | ✅ | 9
|  | 1.19.2: Tenant Activity Table | 3 | ~2h | ✅
|  | 1.19.3: Quick Actions + Platform Alerts sidebar | 3 | ~2h | ✅
Sprint 1 | GT-1.20: Platform Settings Page Full Specification | 1.20.1: Platform settings endpoints | 5 | ~3h | ✅ | 13
|  | 1.20.2: Platform settings UI with 5 tabs | 8 | ~4h | ✅
Sprint 1 | GT-1.21: Tenant Detail Page Setup Progress Section | 1.21.1: Tenant setup progress endpoint | 2 | ~1h | ✅ | 5
|  | 1.21.2: Tenant setup progress UI | 3 | ~2h | ✅
Sprint 1 | GT-1.22: Post-Setup Redirect Logic | 1.22.1: Setup complete returns redirect_to | 1 | ~1h | ✅ | 3
|  | 1.22.2: Frontend post-setup success animation | 2 | ~1h | ✅
Sprint 1 | GT-1.23: OrganizationGroup Configuration (3S Group Entity) | 1.23.1: OrganizationGroup backend fields | 2 | ~1h | ✅ | 8
|  | 1.23.2: POST /api/setup/group endpoint | 3 | ~2h | ✅
|  | 1.23.3: Setup wizard Step 3 "Configure Your Organization" | 3 | ~2h | ✅
Sprint 1 | GT-1.24: Company Domain Field | 1.24.1: Add email_domain to Tenant model | 1 | ~1h | ✅ | 2
|  | 1.24.2: Update Tenant API schemas | 1 | ~1h | ✅
Sprint 1 | GT-1.25: Admin Invitation Workflow | 1.25.1: POST /superadmin/admins/invite endpoint | 5 | ~3h | ✅ | 11
|  | 1.25.2: Admin invitation email | 3 | ~2h | ✅
|  | 1.25.3: Invite Admin UI | 3 | ~2h | ✅
Sprint 1 | GT-1.26: Test Azure Entra ID Connection | 1.26.1: POST /superadmin/tenants/{id}/test-entra endpoint | 2 | ~1h | ✅ | 4
|  | 1.26.2: Test Connection button UI | 2 | ~1h | ✅
Sprint 1 | GT-1.27: Admin Password Set / First-Login Flow | 1.27.1: Password set token system | 3 | ~2h | ✅ | 9
|  | 1.27.2: POST /auth/set-password endpoint | 3 | ~2h | ✅
|  | 1.27.3: /set-password UI page | 3 | ~2h | ✅
Sprint 1 | GT-1.28: Super Admin Audit Log | 1.28.1: SuperAdminAuditLog table | 3 | ~2h | ✅ | 12
|  | 1.28.2: Audit logging middleware | 3 | ~2h | ✅
|  | 1.28.3: GET /superadmin/audit-log endpoint | 3 | ~2h | ✅
|  | 1.28.4: Audit log UI page | 3 | ~2h | ✅
Sprint 1 | GT-1.29: Seat Limit Enforcement | 1.29.1: Seat limit check in enrollment API | 2 | ~1h | ✅ | 4
|  | 1.29.2: Seat limit warning events | 2 | ~1h | ✅
Sprint 1 | GT-1.30: Company Suspension Notification | 1.30.1: tenant.suspended event | 3 | ~2h | ✅ | 6
|  | 1.30.2: Email notification on suspension | 3 | ~2h | ✅
Sprint 1 | GT-1.31: Create New User During Admin Assignment | 1.31.1: Create User form in Assign Admin page | 4 | ~2h | ✅ | 7
|  | 1.31.2: Create User API endpoint | 3 | ~2h | ✅

## Sprint 2
Sprint | General Task | Detailed Task | Story Points | Effort | Status | Total SP (GT)
Sprint 2 | GT-2.1: Course Management | 2.1.1: Course CRUD API | 5 | ~3h | ✅ | 50
|  | 2.1.2: Module & Lesson API | 5 | ~3h | ✅
|  | 2.1.3: Database models (PostgreSQL) | 3 | ~2h | ✅
|  | 2.1.4: Course publish/unpublish toggle | 2 | ~1h | ✅
|  | 2.1.5: Course assignment with deadline | 3 | ~2h | ✅
|  | 2.1.6: Deadline enforcement logic | 3 | ~2h | ✅
|  | 2.1.7: Bulk department-level course assignment | 3 | ~2h | ✅
|  | 2.1.8: Quiz/Assessment CRUD | 5 | ~1h | ✅
|  | 2.1.9: Assessment taking and scoring | 3 | ~2h | ✅
|  | 2.1.10: Course preview mode | 3 | ~2h | ✅
|  | 2.1.11: Course rating and review | 3 | ~2h | ✅
|  | 2.1.12: Course/lesson bookmarking | 6 | ~4h | ✅
|  | 2.1.13: Certificate generation, integrity, and download | 6 | ~4h | ✅
Sprint 2 | GT-2.2: Content Ingestion Pipeline | 2.2.1: AGNO workflow for content ingestion | 5 | ~3h | ✅ | 8
|  | 2.2.2: MinIO file upload integration | 3 | ~2h | ✅
Sprint 2 | GT-2.3: Enrollment & Progress | 2.3.1: Enrollment API | 3 | ~1h | ✅ | 16
|  | 2.3.2: Progress tracking API | 5 | ~3h | ✅
|  | 2.3.3: Video and text progress heartbeat APIs | 5 | ~3h | ✅
|  | 2.3.4: Timezone-aware streak and XP calculation | 3 | ~2h | ⏳
Sprint 2 | GT-2.4: RabbitMQ Inter-Service Events | 2.4.1: Lesson completion event | 2 | ~1h | ✅ | 4
|  | 2.4.2: Enrollment event | 2 | ~1h | ✅
Sprint 2 | GT-2.5: Frontend UI — Course Pages | 2.5.1: Course Catalog page scaffold | 5 | ~3h | ✅ | 23
|  | 2.5.2: Course Detail page with API integration | 5 | ~3h | ✅
|  | 2.5.3: Learning Player page | 5 | ~3h | ✅
|  | 2.5.4: Onboarding wizard UI | 5 | ~3h | ✅
|  | 2.5.5: Video player heartbeat integration (frontend) | 3 | ~2h | ✅
Sprint 2 | GT-2.6: AI UI Scaffold — Chat Coach, Recommendations, Skill Gap (activates in Sprint 4) | 2.6.1: Chat Coach interface scaffold [AI UI Scaffold — activates in Sprint 4] | 3 | ~2h | ✅ | 5
|  | 2.6.2: Recommendations panel scaffold [AI UI Scaffold — activates in Sprint 4] | 2 | ~1h | ✅
Sprint 2 | GT-2.7: Testing — Learning Platform | 2.7.1: Course service unit tests | 5 | ~3h | ⏳ | 11
|  | 2.7.2: Identity + Learning integration test | 3 | ~2h | ⏳
|  | 2.7.3: Content ingestion integration test | 3 | ~2h | ⏳
Sprint 2 | GT-2.8: Multi-Tenant Learning Platform | 2.8.1: Add tenant_id to learning entities | 5 | ~3h | ⏳ | 17
|  | 2.8.2: Tenant-scoped course catalog | 3 | ~2h | ⏳
|  | 2.8.3: Tenant-scoped enrollment and progress | 3 | ~2h | ⏳
|  | 2.8.4: MinIO tenant-prefixed paths | 3 | ~2h | ⏳
|  | 2.8.5: Tenant-scoped gamification | 3 | ~2h | ⏳

## Sprint 3
Sprint | General Task | Detailed Task | Story Points | Effort | Status | Total SP (GT)
Sprint 3 | GT-3.1: Gamification System (XP, Levels, Badges, Streaks, Leaderboard) | 3.1.1: XP and Level system | 5 | ~3h | ✅ | 14
|  | 3.1.2: Badges and Achievements | 3 | ~2h | ✅
|  | 3.1.3: Streak tracking | 3 | ~2h | ✅
|  | 3.1.4: Leaderboard API | 3 | ~2h | ✅
Sprint 3 | GT-3.2: Team Management | 3.2.1: Team CRUD API | 3 | ~2h | ⏳ | 14
|  | 3.2.2: Team membership | 3 | ~2h | ⏳
|  | 3.2.3: Team activity feed | 2 | ~1h | ⏳
|  | 3.2.4: Team course assignment | 3 | ~2h | ⏳
|  | 3.2.5: Member progress view | 3 | ~2h | ⏳
Sprint 3 | GT-3.3: Goals Tracking | 3.3.1: Personal goals API | 3 | ~2h | ⏳ | 5
|  | 3.3.2: Team goals API | 2 | ~1h | ⏳
Sprint 3 | GT-3.4: Skill Gap Analysis (pg0 relational queries) | 3.4.1: Skill graph in PostgreSQL | 5 | ~3h | ⏳ | 8
|  | 3.4.2: Gap computation | 3 | ~2h | ⏳
Sprint 3 | GT-3.5: RabbitMQ Event Flow | 3.5.1: Gamification events publisher | 3 | ~2h | ⏳ | 6
|  | 3.5.2: Socket.io consumer integration | 3 | ~2h | ⏳
Sprint 3 | GT-3.6: Frontend UI — Gamification, Teams, Goals | 3.6.1: Leaderboard page | 5 | ~3h | ✅ | 25
|  | 3.6.2: Profile page with gamification widgets | 5 | ~3h | ⏳
|  | 3.6.3: Real-time Socket.io integration for gamification | 3 | ~2h | ⏳
|  | 3.6.4: Teams page | 3 | ~2h | ⏳
|  | 3.6.5: Goals page | 3 | ~2h | ⏳
|  | 3.6.4: Teams page | 3 | ~2h | ⏳
|  | 3.6.5: Goals page | 3 | ~2h | ⏳
Sprint 3 | GT-3.7: AI UI Scaffold — Skill Gap Dashboard (activates in Sprint 4) | 3.7.1: Skill Gap Dashboard scaffold [AI UI Scaffold — activates in Sprint 4] | 3 | ~2h | ⏳ | 3
Sprint 3 | GT-3.8: Testing — Gamification & Teams | 3.8.1: Gamification service unit tests | 5 | ~3h | ⏳ | 11
|  | 3.8.2: Learning + Gamification integration test | 3 | ~2h | ⏳
|  | 3.8.3: Socket.io notification flow test | 3 | ~2h | ⏳
Sprint 3 | GT-3.7: Multi-Tenant Gamification & Teams | 3.7.1: Tenant-scoped teams | 3 | ~2h | ⏳ | 5
|  | 3.7.2: Tenant-scoped goals | 2 | ~1h | ⏳

## Sprint 4
Sprint | General Task | Detailed Task | Story Points | Effort | Status | Total SP (GT)
Sprint 4 | GT-4.1: AI Agents Service Core | 4.1.1: Initialize AI Agents Service | 3 | ~2h | ⏳ | 13
|  | 4.1.2: GROQ integration | 5 | ~3h | ⏳
|  | 4.1.3: AGNO agent runtime setup | 5 | ~3h | ⏳
Sprint 4 | GT-4.2: Hindsight Memory System | 4.2.1: Hindsight setup | 3 | ~2h | ⏳ | 9
|  | 4.2.2: Memory API endpoints | 3 | ~2h | ⏳
|  | 4.2.3: Per-agent memory bank configuration | 3 | ~2h | ⏳
Sprint 4 | GT-4.3: Chat Coach Agent (Agent 1) | 4.3.1: Chat Coach AGNO agent | 3 | ~2h | ⏳ | 9
|  | 4.3.2: Chat API endpoints | 3 | ~2h | ⏳
|  | 4.3.3: Real-time Socket.io streaming | 3 | ~2h | ⏳
Sprint 4 | GT-4.4: Recommendation Agent (Agent 2) | 4.4.1: Recommendation AGNO agent | 3 | ~2h | ⏳ | 6
|  | 4.4.2: Recommendations API | 3 | ~2h | ⏳
Sprint 4 | GT-4.5: Remaining Agents (Agents 3–6) | 4.5.1: Gamification AGNO agent (Agent 3) | 5 | ~3h | ⏳ | 20
|  | 4.5.2: Course Maker AGNO agent (Agent 4) | 5 | ~3h | ⏳
|  | 4.5.3: Content Librarian AGNO agent (Agent 5) | 5 | ~3h | ⏳
|  | 4.5.4: Skill Gap Analyzer AGNO agent (Agent 6) | 5 | ~3h | ⏳
Sprint 4 | GT-4.6: AGNO Team Workflow Integration | 4.6.1: Inter-agent team workflows | 3 | ~2h | ⏳ | 6
|  | 4.6.2: RabbitMQ event routing for agents | 3 | ~2h | ⏳
Sprint 4 | GT-4.7: Frontend UI — Wire AI Scaffolds to Live APIs | 4.7.1: Wire Chat Coach UI to live API | 3 | ~2h | ⏳ | 16
|  | 4.7.2: Wire Recommendations panel to live API | 3 | ~2h | ⏳
|  | 4.7.3: Wire Skill Gap Dashboard to live API | 5 | ~3h | ⏳
|  | 4.7.4: Dashboard page with AI widgets | 5 | ~3h | ⏳
Sprint 4 | GT-4.8: Testing — AI Agents | 4.8.1: Agent service unit tests | 3 | ~2h | ⏳ | 10
|  | 4.8.2: Learning + Agents integration test | 3 | ~2h | ⏳
|  | 4.8.3: Chat Coach end-to-end flow test | 2 | ~1h | ⏳
|  | 4.8.4: Hindsight memory persistence test | 2 | ~1h | ⏳
Sprint 4 | GT-4.11: Multi-Tenant AI Agents | 4.11.1: RabbitMQ event payload tenantId | 3 | ~2h | ⏳ | 13
|  | 4.11.2: Tenant-scoped Chat Coach | 3 | ~2h | ⏳
|  | 4.11.3: Tenant-scoped Recommendations | 2 | ~1h | ⏳
|  | 4.11.4: Tenant-scoped Skill Gap | 2 | ~1h | ⏳
|  | 4.11.5: Demo mode with seeded tenants | 3 | ~2h | ⏳

## Sprint 5
Sprint | General Task | Detailed Task | Story Points | Effort | Status | Total SP (GT)
Sprint 5 | GT-5.1: Analytics Service | 5.1.1: Analytics dashboards API | 3 | ~2h | ⏳ | 12
|  | 5.1.2: AGNO batch workflow for analytics | 3 | ~2h | ⏳
|  | 5.1.3: Per-department analytics | 3 | ~2h | ⏳
|  | 5.1.4: Export analytics report | 3 | ~2h | ⏳
Sprint 5 | GT-5.2: Notification Service | 5.2.1: Email notifications | 3 | ~2h | ⏳ | 9
|  | 5.2.2: Real-time Socket.io notifications | 3 | ~2h | ⏳
|  | 5.2.3: Notification preferences and routing | 3 | ~2h | ⏳
Sprint 5 | GT-5.3: Frontend UI — Dashboard, Analytics, Integration Polish | 5.3.1: Dashboard page | 3 | ~2h | ⏳ | 18
|  | 5.3.2: Analytics page | 3 | ~2h | ⏳
|  | 5.3.3: Teams page | 3 | ~2h | ⏳
|  | 5.3.4: Goals page | 3 | ~2h | ⏳
|  | 5.3.5: Notification center component | 3 | ~2h | ⏳
|  | 5.3.6: Demo mode UI fallbacks | 3 | ~2h | ⏳
Sprint 5 | GT-5.4: Testing — End-to-End Full-Stack Flows & Demo Reliability | 5.4.1: Authentication E2E flow test | 3 | ~2h | ⏳ | 14
|  | 5.4.2: Course lifecycle E2E flow test | 3 | ~2h | ⏳
|  | 5.4.3: AI Coach E2E flow test | 3 | ~2h | ⏳
|  | 5.4.4: Demo reliability stress test | 2 | ~1h | ⏳
|  | 5.4.5: Hindsight memory persistence test | 3 | ~2h | ⏳
Sprint 5 | GT-5.5: Deployment to Docker | 5.5.1: Docker images and Compose finalization | 2 | ~1h | ⏳ | 4
|  | 5.5.2: Local deployment verification | 2 | ~1h | ⏳
Sprint 5 | GT-5.6: Demo Preparation | 5.6.1: Demo script | 3 | ~2h | ⏳ | 6
|  | 5.6.2: Fallback scenarios and seed data | 3 | ~2h | ⏳
Sprint 5 | GT-5.5: Multi-Tenant Final Integration | 5.5.1: Super Admin analytics dashboard | 5 | ~3h | ⏳ | 13
|  | 5.5.2: Multi-tenant E2E tests | 3 | ~2h | ⏳
|  | 5.5.3: Tenant isolation regression tests | 3 | ~2h | ⏳
|  | 5.5.4: Final demo with 2 tenants | 2 | ~1h | ⏳